Outcome Report of 
National Networked Digital Library, Indonesia

Reporting Period: November 24, 2000 - May 24, 2001
By Ismail Fahmi, ST - ismail@itb.ac.id

A project undertaken by Computer Network Research Group (CNRG) and Knowledge Management Research Group (KMRG) ITB, funded by IDRC Canada under its Pan Asia Networking R&D Grants Program, and Yayasan Litbang Telekomunikasi dan Informatika. Web site: http://idln.itb.ac.id.

### Abstract

This project, national networked digital library in Indonesia, initially had objectives that were limited only for research and education (university) institution. Resources that will be managed were only research reports, theses, and dissertation. And the expected impact also were limited to increase the utilization of researches result and to push the electronic scholarly publishing.

But in the first seminar and workshop for the socialization of its idea, people suggested not to restric this effort on such objectives only. Many non research and education institution also showed their interest to join the network, such as from NGO, high school, bussiness, public organization, and so on. Finally we tried to accomodate their interest and broaden the scope of institution that can join the network and the resources type that will be managed.

The results was very impressive. We established the Indonesian Digital Library Network (IndonesiaDLN) community. Partners of the network can be from personal, internet cafe, and any institution or organization. Any types of knowledge are accepted. And finally this network seems to have an ambitious mission: connecting people's knowledge and creating one (distributed-and-networked) big national memory.

Ganesha Digital Library is one of this project result. It is the first web-based digital library application that will be distributed as an open-source in Indonesia. People can get the source code and install the application in their computer freely but in one condition: They should agree to share their knowledge that are managed using GDL to human being within IndonesiaDLN. This condition is one of our campaign about knowledge sharing.

GDL will become the application that will be installed for IndonesiaDLN hub server and GDL Hub server. It also can be configured for personal, internet cafe, and institution purposes wheter with dedicated or temporary connection. This is one of our strategy to disseminate and utilize knowledge to our nation: give the easiest and personal touch way for people in joining the network.

### Objectives

The objectives of this project are:

- develop a digital library network system that suitable for internet infrastructure of developing countries especially Indonesia;

- develop an Indonesian Digital Library Network (IDLN);

- facilitate efforts of universities to develop their own digital library system and to have students and researchers submit their research reports, theses, and dissertations;

- install and operate IDLN servers so that students, researchers, and others engaged in scholarship can search, browse, and retrieve electronic reports;

- prepare training and course material to support the development of IDLN;

- push forward the revolution in electronic scholarly publishing so that it may lead to universities playing a more active and cost-effective role in the production, organization, preservation and dissemination of knowledge

### Related Previous Activities

This project can't be separated from its previous activities. The development of digital library by ITB actually have been started since in the middle of 1999 (version 1.0 and 2.0). And at the beginning of 2000, the development of Ganesha Digital Library (GDL) version 3.0 is started. This version become the major part of further development of digital library system in this project.

The following are activities undertaken related to GDL version 3.0 and the establishing of IndonesiaDLN.

- Adopting Dublin Core Metadata Standard.
In GDL version 1 and 2, we didn't use any standard for metadata. Starting from version 3.0 we want to adopt the widely used metadata standard for electronic resources. It is Dublin Core Metadata Element Set Version 1.1. This will lead to the opportunity of international collaboration for digital library network.

- Writing the Code
The design of GDL 3.0 system was completely different from its former version. We should rewrite the code from scratch. The code  was in PHP scripting language.

- Test Bed and Implementation
GDL 3.0 was successfully tested and implemented on top of FreeBSD server box. The server application were using Apache web server, mysql database server, dan swish-e search engine. We used qmail as the mail transport agent for more reliability and security.

Ten librarians of ITB Central Library were trained to operate the system such as for administrator, knowledge officer, administrator, digitizer, and operator. During this experiment, they uploaded collection of research reports, final projects (undergraduate), theses, and dissertations. We also tried to upload multimedia file such as audio and video.

The URL of the digital library server is http://digilib.itb.ac.id. (Currently running GDL version 3.1)

- Developing IndonesiaDLN Web Site
Although this project administratively just started on November 2000, we have done some important activities several months before. On August 2000, web develop IndonesiaDLN web site to disseminate the idea, activities, and progress of this project. This web site was very usefull for Indonesian librarian and IT engineer that want to collaborate with us in developing digital library network.

The site was carried out with the help of aid from IDRC and YLTI. The URL is http://idln.itb.ac.id.

- Launching and National Seminar
At October 2, 2000, ITB First Vice Rector launched the digital library web site in a national seminar of digital library. The seminar was held by ITB Central Library jointly with CNRG and KMRG ITB. About 250 participants from all over Indonesia attended the seminar.

It was a very good chance to disseminate the result of the project and to spread the idea of developing National Networked Digital Library in Indonesia. Principal investigator of this project (Ismail Fahmi) gave presentation about progress of Ganesha Digital Library and objective of the project to develop the network. As the follow up, a two days meeting was held after the seminar.

- Meeting for Establishing IndonesiaDLN
After the seminar we held a meeting that was attended by 40 representatives from 23 research and education institutions in Indonesia. The meeting was very important because resulted the following agreements:

  - Establishing a community named Indonesian Digital Library Network or IndonesiaDLN. The abbreviation of IDLN has been exist for Indonesian Distance Learning Network. So then we used IndonesiaDLN for this network.

  - Elect the general secretary (Ismail Fahmi) and the office of IndonesiaDLN at ITB.

  - Using Dublin Core Metadata Element Sets Version 1.1 as the base of IndonesiaDLN Metadata Standard.

  - Approving IndonesiaDLN Metadata Standard to be used by any digital library application within IndonesiaDLN.

  - Using XML format for data interchange among digital library servers.

The complete result of this meeting can be downloaded from http://idln.itb.ac.id/meeting/Oktober2000/IndonesiaDLN-hasil-meeting-2okt2000.pdf (132 kb).

- Getting Funding for Implementation of Digital Library at Eastern Indonesian Universities (EIUDLN)
The meeting also was attended by representatives from three institutions at Eastern Indonesia; University of Cendrawasih Irian Jaya, University of Hasanuddin Makassar, and University of Haluoleo Kendari. Mr. Nello Angerilli from EIUDP/CIDA-Project also attended the meeting. 

In the meeting we had a limited discussion with them, and we came to an agreement to develop digital library network at the universities with the aid from EIUDP/CIDA-Project.

We did the activities as part of this project, although the Memorandum of Grant Condition with IDRC just signed up on November 2000. It was because the most important event of this project to develop National Networked Digital Library in Indonesia was done there.

### Activities Undertaken During the Initial 6 Months

Since November 24th, 2000 until May 23th, 2001 we have done the following activities:

- Registering internet domain for IndonesiaDLN
Domain name for IndonesiaDLN is IndonesiaDLN.org. We have registered the domain and the primary DNS server is located at ITB Central Library. The IndonesiaDLN hub server, GDL Hub server, and other related server of IndonesiaDLN will use the domain. Such as gdlhub.IndonesiaDLN.org, hub.IndonesiaDLN.org, www.IndonesiaDLN.org, and so on.

- Procurement of PC Workstation
We have procured three personal computers to support development of GDL, creating CD-ROM, researching multimedia techniques for knowledge distribution, and for administration of GDL-Network and IndonesiaDLN Hub server. These workstations are located at KMRG ITB lab within ITB Central Library.

- Designing GDL 3.1 to support IndonesiaDLN Metadata Standard
We have changed the design of GDL 3.0 to be more portable, easy to implement and replicate, and of course support IndonesiaDLN Metadata Standard. GDL 3.1 now fully utilizes the database access to  create and display metadata, create directory tree, and search. GDL 3.1 also should be expandable to support large hard disk capacity (scalability).

GDL 3.1 can be installed on Windows 9x/NT/2000 and on Linux/Unix server. We keep using server application such as apache, mysql, and php.

- Designing GDL-Network System
We have some consideration in designing networking system for GDL-Network, namely:

  - condition of telecommunication infrastructure in Indonesia (internet bandwith and availability)

  - existing infrastructure of computer and network within our community

  - psicological aspect of the system that should able to attract poeple to join IndonesiaDLN and share their knowledge.

From above considerations, we developed the following design:

  - GDL-Network is a network of digital library servers that use GDL as the application.

  - There will be a GDL Hub server at central side that acts as a concentrator and moderator for communication among GDL partner servers.

  - There will be GDL partner server at partner side that will be used to manage their (community's) knowledge.

  - There will be GDL partner server for personal, internet cafe, and institution.

  - Communication between GDL Hub and Partner will use HTTP and/or SMTP protocol.

  - GDL will support roaming membership. It means user can register to be a member from any GDL partner server, and they can use the account at any GDL partner servers without have to register again.

  - CD-ROM transfer will be used as communication media between hub and partner that have no internet connection (ie at rural area).

- Designing Interchange Protocol Using SMTP and HTTP
There are two mode of data interchange protocol between GDL Hub and Partner, that are SMTP and HTTP mode.

SMTP protocol will be implemented on Unix platform. If partner uses unix box for GDL, data synchronization can be done automatically without need any administrator involvement. 

HTTP protocol will be implemented for both unix and windows. Administrator (personal, internet cafe, or institution) can do synchronization via web pages. Both hub and partner servers will communicate on administrator's demand using HTTP connection.

Information that will be synchronized are metadata, files, publisher, and membership. By membership synchronization, member will gain the roaming membership facilities.

- Writing the Code and Web Design
Most of codes in GDL 3.1 are written from scratch to fit the design requirements. Some modules are taken from previous version. Web code are using PHP scripting language with XML and GD (gif drawing) modules are enabled. Web design uses simple and minimal model. User can access the pages fast and easily. 

Communication protocol using SMTP are being developed using C++ language.

We use windows 98 and Unix FreeBSD operating system during the system development.

- Debugging and Testing
Bugs always appear time by time. We spent most of the time to find the bugs and fix them. GDL 3.1 has been tested on windows 98 and Linux/Unix FreeBSD. 

We have successfully tested the operation of client-server communication using HTTP protocol. While the SMTP protocol communication is not finished yet. Test bed has been done for synchronization between ITB Central Library DL server and GDL Hub (in the same network) and between University of Muhammadiyah Malang (East Java) and GDL Hub (West Java). Metadata from the university has successfully uploaded into GDL Hub using HTTP protocol.

- Implementation
Currently we have deployed the following GDL servers:

Hub servers:

  - IndonesiaDLN Hub server, http://hub.indonesiaDLN.org

  - GDL-Network Hub server, http://gdlhub.indonesiaDLN.org

Institutional servers (probably some sites can't be opened at this moment, due to the test bed phase):

  - ITB Central Library, http://digilib.itb.ac.id

  - Post Graduate Program of ITB, http://digilib.pps.itb.ac.id.

  - University of Muhammadiyah Malang, http://digilib.umm.ac.id

  - Badan Litbang Kesehatan Depkes Jakarta, http://digilib.litbang.depkes.go.id

  - Atma Jaya Catholic University, http://digilib.atmajaya.ac.id

  - Salman Mosque of ITB, http://digilib.salman.itb.ac.id

  - Bina Nusantara University, http://digilib.binus.ac.id

  - Magister Management of Agribussiness IPB, http://digilib.mma.ipb.ac.id

  - University of Cendrawasih Irian Jaya (off line)

  - University of Hasanuddin Makassar (off line)

  - University of Haluoleo Kendari (off line)

Internet Cafe servers (no url needed):

  - Pointer Indonesia (JBWNPOINTER)

Personal server (no url needed):

  - Dr. Onno W. Purbo (JKPEONNO)

  - Dr. Budi Rahardjo (JBPEBR)

  - Ismail Fahmi (JBPEISMAIL)

We also have successfully deploy GDL that contain metadata collections for running on CD-ROM. This will be useful for knowledge distribution using CD-ROM.

- Procurement of Servers
We have procured two servers for GDL Hub server and IndonesiaDLN Hub server. Both servers will act as backup each other. Currently the servers will be placed at AI3 (Asian Internet Interconnection Initiatives) ITB NOC. In the future we plan to offer cooperation with ISP that interested to provide free server hosting for the server.

Specification of the servers are similar, that is:

Mainboard Intel Serverboard STL2
Dual Processor Intel P!!! 933Mhz
ECC SDRAM 256MB
Hard drive Seagate Barracuda SCSI 18GB
Hard drive Seagate Barracuda IDE 40GB

- Distributing GDL Brochure
We made a brochure of GDL both printed (lux) and electronic to be disseminated nationally. The brochure will be published initially on the seminar (6-7 June 2001). Electronic version of the brochure can be downloaded at http://gdlhub.indonesiaDLN.org/doc/brosur-gdl31.pdf.

- Creating CD-ROM Distribution of GDL
GDL will be distributed as open-source. The source code of GDL totally is only about 2 MB. But for user confenience we include the apache, mysql, and php source code and binary in the CD-ROM both for windows and unix. 

Although it is an open-source, we don't place the source-code of GDL openly at an FTP server. People that want to get the code have to submit an application form. They have to sign that they agree to share their knowledge managed using GDL into IndonesiaDLN. Information about getting the source code can be found at http://gdlhub.IndonesiaDLN.org/faqgdl.php.

- Preparing International Seminar and IndonesiaDLN 2nd Workshop
Currently, we are overkilled by preparation for the seminar and workshop on next June 2001 (6-9 June). Information about this seminar and workshop can be found at http://idln.itb.ac.id. 

In the seminar, we will lauch the IndonesiaDLN network. We will inform the vision, startegy, and practical aspect of IndonesiaDLN, and open the registration to become IndonesiaDLN partner.

In the workshop, we will meet with IndonesiaDLN partner to discuss metadata standard, current application of digital library, the organization, membership, and so on. Such a meeting can be an annual meeting of IndonesiaDLN in the future.

### Other Related Activities During the Initial 6 Months

Besides above activities, we note some activities that related to this project. The following are titles of the activities:

- Cooperation with Indonesian Legal Aid Institution and EIUDP to develop system for Human Right Network. This network will be integrated with IndonesiaDLN network.

- Signing MOU with YLTI to develop Networked Information System for SME. This effort will be integrated with IndonesiaDLN network.

- Signing MOU with McGill for Survey and Consultation on developing digital library network among IAIN, Islamic Religion Institutions.

- Conduct site survey for 11 IAINs.

- Present the survey report to McGill and MORA (Ministry of Religion Affair) of Indonesia.

- Procurement of equipment for EIUDLN.

- Pre-Installation of GDL for EIUDLN.

### Results Obtained

The following is table of the results obtained during the activities according to the expected outcomes as stated in the project proposal.

| No | Outcome types | Expected | Fact |
| --- | --- | --- | --- |
| 1 | Standardization | Standard for: - Metadata and classification - Submission, authentication, and dissemination process | Achieved: - Metadata Standard for IndonesiaDLN based on Dublin Core Metadata Element set version 1.1 was approved. Not implemented: - Classification of categories and subject is not practical. No standard was approved for this subject. - Submission, authentication and dissemination are vary according to the system and environtment. Developing a standard for this is not practical. Conclusion: - This outcome is considered to be achieved. |
| 2 | Servers | Servers that will be installed and operated: - A central server at AI3 ITB NOC. - 7 partner servers at: Pasca Sarjana ITB, ITB Central Library, Research Institute of ITB, University of Brawijaya Malang, University of Muhammadiyah Malang, IAIN Sunan Ampel Surabaya, University of Cendrawasih Irian Jaya. | The installed servers: - 2 central server at AI3 ITB NOC: GDL Hub server and IndonesiaDLN Hub server. - 15++ partner servers are installed. See the list above. Conclusion: - This outcome is excel the target. - It shows that many Indonesian institutions (research, education, etc) are interested to join this efforts. - It is a good weather for the future of IndonesiaDLN. |
| 3 | Organization | - A central agency will be established to organize the operational and administration of the network. The central agency will be in ITB. - Other agencies or representations will be established in each partner that install and operate a partner server (i.e. at Unibraw, UMM, IAIN, and UNCEN). - The coordination of all agencies especially for information exchange and library network will be established and managed by the central agency. | Achieved: - IndonesiaDLN was established as an open community of digital library network in Indonesia. The central administration office is located at KMRG ITB. - Members of IndonesiaDLN are not limited to research and education institution. Even any organization or individual are welcame to join this network. Not yet achieved: - Representation of IndonesiaDLN at each region is not yet discussed. This will become a major issue in the next workshop (8-9 June 2001). - The coordination scheme also not yet defined. Conclusion: - Half of the expected outcome has been achieved. - The rests are expected to be achieved later. - Scope of the involved partner is widened. |
| 4 | Collections | At the end of the project, we estimate the participation from students and researchers will be: - At least 5% of full text of final reports, theses, and dissertations of a graduation period of ITB during the project will be submitted into central server. - At least 5% of full text of research reports managed by Research Institution (LP) of ITB will be uploaded into central server. | Achieved: - Currently, knowledge type that will be managed by IndonesiaDLN are not limited to research reports, final projects, theses, and dissertations. But at this moment, such resources will dominate the collections. - Type of collections that will be managed: Undergraduate Theses, Master Theses, PhD Theses, Article/Grey literature, Clipping, Course Material, Distance Learning, Examination & Quiz Sample, Expertise Directory, Free e-Books, Internet Directory, Journal, Multimedia, Proceeding, Publication, Research Report, and Heritage. - Current collections are about 550 title totally. Most of them are research reports, theses, dissertation, and multimedia. - Partners are now starting to upload their resources into their own digital library server. Not yet achieved: - Submission has not widely done by students, but mostly by librarian. It is because of the trial phase. Conclusion: - The target for collection captured is not yet achieved yet. It should be continued at the second phase of this project. - Socialization of the digital library services should be done attractively to communities member. |
| 5 | Dissemination | - Other installed partner servers will be able to replicate the database from central server for their local dissemination. - Dissemination using CD-ROM will be done for eastern Indonesia universities. | Achieved: - ITB Central Library and University of Muhammadiyah Malang have successfully done test-bed for metadata synchronization. - Personal and Internet Cafe partner server also have been able to download metadata using HTTP protocol. - Limited CD-ROM dissemination has been done for some partners. It contain the source-code of GDL. Not yet achieved: - CD-ROM dissemination to the 'off-line' servers. Conclusion: - The current contents are not too worth to be disseminated using CD-ROM. - We will do this at second phase of this project. |

Ganesha Digital Library Features

The following are lists of GDL features:

- Distributed Knowledge Management

- Centralized Knowledge Distribution

- Online Member Registration

- Roaming Membership

- Search and Browse

- Category-based Organization

- Upload Metadata and Files

- Personal Directory

- Review Forum

- Access Restriction

- Image Thumbnail

- Knowledge Organization

- News

- Synchronization

- Member and Group Administration

- Advertisement

- Dublin Core / IndonesiaDLN Metadata Compliant

- XML Based Transaction

- Running on CD-ROM

Some GDL Snapshots

The following are collection of GDL screen pictures. They show the user interface of front-page and inner pages. Also the verbose display of synchronization processes.

The life system can be accessed at http://gdlhub.indonesiaDLN.org or http://digilib.itb.ac.id.

Picture 1

Picture 2

### Second Half Year Plan

During

the period of 25th May 2001 - 24th November 2001 we plan to conduct the following activities:

- Socialization of GDL-Network to ITB civitas academica (29th May 2001).

- International Seminar on Knowledge Management and Digital Library together with the launching of Indonesian Digital Library Network (6-7 June 2001).

- IndonesiaDLN second workshop (8-9 June 2001).

- Writing GDL documentation and user guide.

- Deployment and training for Eastern Universities (end of June 2001).

- Deployment and training for 13 IAIN (depending on MORA approval).

- Deployment and training for new partners.

- Reserch multimedia presentation of some digital library content for distribution using CD-ROM or VCD.

- Seminar Digital Library Friendly for Children (August 2001).

- Dissemination of digital libra

- ry content using CD-ROM.

* Author is head of KMRG ITB and currently is the general secretary of  IndonesiaDLN.