DONOR MATRIX

Donor Matrix is compiled using the Template of the Action Plan

FIVE – YEAR ACTION PLAN

FOR THE DEVELOPMENT AND IMPLEMENTATION

OF INFORMATION AND COMMUNICATION TECHNOLOGIES (ICT) IN INDONESIA

Government of Indonesia’s Action Plan to overcome the Digital Divide, in accordance with the Policy Framework for Development and Implementation of Information and Communication Technologies in Indonesia under

Presidential Instruction No. 6/2001

Note:	The components of the Action Plan related to existing or planned donors’ assistance are highlighted.

1. Policy and Legal Framework

| No. | ## Action Plan | Time Schedule | Priority | Implementing Agency | Donors’ Current Program |
| --- | --- | --- | --- | --- | --- |
| 1.1 1.1.1 | # Policy #### Telecommunications - Improve telecommunication regulatory framework in Indonesia including licensing, tariff, interconnection, standardization, and frequency spectrum management. - Accelerate the enactment of telecommunication related ministerial decrees. - Define universal access policy and targets with concrete implementation measures including the establishment of Universal Service Fund. - Remove barriers to competition in the telecommunications market and facilitate faster integration service safeguards and roll out of telecommunication and internet technologies, including high capacity, broadband services and peer group radio networks. - Accelerate the resolution of KSO problem. - Empower independent regulatory body. - Complete broadcasting bill. | 2001-2002*) 2001*) 2001-2002*) 2001-2003*) 2001-2002*) 2001 2001-2002*) | A A A A A A A | Min. of Communications, TKTI Min. of Communications Min. of Communications, Min. of Finance, TKTI, Telecommunication Operators Min. of Communications Min. of Communications, PT.Telkom, KSOs Min. of Communications Min. of Communications, TVRI, RRI | WB: (a) Telecommunications Sector Modernization Project. 3 reform elements: (i) entry of world class operators, (ii) competition in all segments of the sector, and (iii) reorganization of the established public telecommunications service provider. The proposed project has a policy component, an investment component, and a technical assistance component. (b) On-going dialogue on overall sector development including: market structure, regulatory development, and rural telecom. (c) Technical assistance on regulatory development and accelerated rural access. USAID: (a) Assessment of Indonesia’s ICT Needs: provides a countrywide internet sector overview, analysis of constraints and opportunities, and recommendations on four key areas – telecommunications and e-commerce policy, pipes (infrastructure), private sector, people (human resources) – ‘the 4P’s framework’ to be the basis for USAID ICT working group activities. (b) On-going assistance for the implementation of Telecommunications Law No. 36/1999: (i) sponsor seminars and roundtable discussions, and (ii) technical advice on: (1) the establishment of an independent regulatory body for telecommunications, (2) benchmark interconnection rates and a long-run incremental cost model for setting rates in the future, (3) technologically neutral policies for voice over the Internet, (4) a universal service program for Indonesia, (5) the broadcasting bill drafted by Commission I of Parliament. Japan: (a) Assigned Senior Advisor for ICT to assist and give policy recommendations for the ICT Policy Framework and Action Plan, (b) Continuing dialogue with GOI: JICA sponsored video conference with TKTI and sent mission dialogues throughout the year. CIDA: Advisory assistance to Bappenas Deputy for Production Trade and Infrastructure under “Infrastructure Policy and Advisory Support to Sector Reorientation and Private Engagement in Infrastructure Provision under Decentralization”. AUSAID: Launched Virtual Colombo plan: Indonesia bilateral program in April 2001 – the basis of AUSAID ICT activities in Indonesia covering legal reform, capacity building for decentralization and education. |
| 1.1.2 | # Information Technology - Develop awareness and educational campaign on ICT for GOI officials and legislators. - Prepare regulations for intra government communication and disclosure. - Prepare regulations for prescribing public information access and online services / procedures to improve service levels, transparency and good governance in government and public institutions. - Prepare regulation accommodating ICT local industry access to the government procurement. - Adopt, adapt, and apply common data interchange standards and common content specification to support interoperability of data integration for common public sectors and interacting business sector needs. - Eliminate any restrictions on ICT investment and reduce burdensome bureaucratic procedures imposed on domestic and foreign investors. - Remove luxury sale tax, as well as other taxes and charges, imposed on an expanded range of ICT products and services. - Remove regulatory and institutional barriers to applying innovative technologies such as wireless, high speed data transfer, and VoIP from standard phones to provide an additional low cost service. - Strengthen commitment to MRA (Mutual Recognition Arrangement) implementation support project of ICT products in APEC Telecommunication and Information Working Group. - Reinforce and update intellectual property definition, protection, and compliance assurance measures. - Enhance the development of information content and application industries including the use of open source software. - Build partnership and alliances among private sector participants to build government online platform based on competitive bids. | 2001-2005 2001-2003 2002 2001-2003 2001-2002 2001-2002 2001*) 2001 2001-2003 2001-2003 2001-2003 2001-2002 | A B B A B B A B A A A B | TKTI, All Ministries, Parliament Min. of Administrative Reform, TKTI TKTI Min. of Industry and Trade Min. of Communications, National Standardization Agency, ICT related associations, Bakosurtanal, National Directory Agency Min. of Finance Min. of Industry and Trade, Min. of Finance, Min. of Home Affairs, local governments, ICT related associations Min. of Communications Min. of Industry and Trade, Min. of Communications Min. of Justice, National Police, Attorney Office TKTI, Min. of Industry and Trade, BPPT, private sector Min of Industry and Trade, BPPT, private sector | WB: Information Infrastructure for Development Project – IIDP – (a) Through BAPPENAS, development and socialization of the IT Framework to improve the GOI management of IT investments and procurement, (b) Through MTAC, assistance in SWOT analysis of the software and systems integration services sector, (c) Through DGIP, development of an institutional development plan, assistance in new legislation for Integrated Circuits, Trade Secrets and Industrial Design, and automation of offices. Japan: Four main areas of comprehensive cooperation package announced at the G8 Okinawa Summit in July 2000: (i) raising awareness and contributing intellectually to policy and institution building, (ii) development and training of human resources, (iii) building IT infrastructure and providing assistance for network establishment, and (iv) promoting the use of IT in development assistance. USAID: (a) Facilitating regional ICT strategy and development with West Java focus group. (b) Public awareness campaign by sponsoring: (i) Asia Pacific Telecommunications Forum, (ii) public radio debate on telecommunications competition. (c) Facilitating dialog between GOI, donors and private sector through video conferences including one on telecenter development. |
| 1.1.3 | # E-Commerce - Adopt minimalist e-commerce law, including resolution of web-contract issues such as e-signatures, encryption security, legal validity of electronic information and messages with reference to UNCITRAL, ASEAN, and APEC model laws. - Develop measures to support SMEs’ participation in ICT development, application, and e-commerce. | 2001 2001-2003 | A B | Min. of Justice, Min. of Industry and Trade, Min. of Communications, Lembaga Sandi Negara, TKTI, BPHN Min. of Industry and Trade | WB: (a) Through MTAC, technical assistance to action plan for establishing a national certification infrastructure, including a proposed Digital Signature Law. (b) Support for pilot VOIP to 250 Wartels under IIDP. CIDA: Advisory work on SMEs programs to develop the capacity of SMEs and the local governments; an example is the development of East Indonesia and its infrastructure. USAID: (a) Survey on ‘ICT use by SME exporters’ and ‘E-Commerce study of SMEs’. Plan follow-ups such as public dialogs and pilot projects. (b) Through a separate legal project (ELIPS), provide assistance on the development of programs on e-commerce law in Indonesian universities. |
| 1.2 1.2.1 | # Legal Framework # Information Technology - Finalize Cyber Law and modernize criminal law to cover computer and cyber crime; and the enforceability of electronically made representations and commitments. | 2001-2002 | A | Min. of Justice, Min. of Communications |  |
| 1.2.2 | # E-Commerce - Review and revise tax law to facilitate electronic transactions. - Adopt national legislation on general e-commerce consumer protection. - Adopt a broad online privacy law with prudent safeguards against protection of criminal activities. | 2003 2001-2002 2002-2003 | B B B | Min. of Industry and Trade, Min. of Finance Min. of Industry and Trade, YLKI Min. of Justice, Min. of Communications, Min. of Industry and Trade | WB: Technical assistance on principles, policies and legal recommendations for E-commerce in Indonesia (IIDP). |
| 1.2.3 | # Institutional Development - Strengthen the institutional capacity of TKTI to accomplish its mandate. - Strengthen the frequency spectrum management system in Indonesia including effective frequency management for new multimedia wireless, broadcasting and broadband services and systems; as well as peer group and specified non-commercial / public benefit networks, such as inter and intra government. - Develop an independent regulatory body. - Develop regional IT centers of excellence, e.g. Bali Camp, Bandung Hi-Tech Valley, APEC center for Entrepreneurship. - Establish e-commerce coordinating group that will articulate a national e-commerce vision and harmonize act as a focal point for fostering regional and domestic e-commerce cooperation. | 2001-2003*) 2001-2002 2001-2003 2001-2005*) 2001-2003 | A A A A B | TKTI Min. of Communications, BPPT Min. of Communications, TKTI Min. of Research and Technology, Min. of Industry and Trade, BPPT, local governments, universities, private sector Min. of Industry and Trade, TKTI, private sector | WB: (a) Technical assistance for TKTI on institutional and policy development, (b) Through MTPT, reviewing the management and allocation of radio frequency spectrum to ensure efficient use of the spectrum and appropriate use of modern technology. USAID: (a) Informal roundtables at DG Postel, topics include: telecommunication licensing, interconnection, pricing policies, frequency allocation, universal service, and the establishment of an independent regulatory process. (b) Public dialogue on an ‘independent regulatory body’. |

- Human Capacity Building

| No. | ## Action Plan | Time Schedule | Priority | Implementing Agency | Donors’ Current Program |
| --- | --- | --- | --- | --- | --- |
|  | - Establish policy to stimulate R&D in ICT in the private sector and in partnership with universities and public institutions. - Develop collaboration between ICT industry and ICT educational institutions through training and R&D collaboration; and form a network for skill and capacity development. - Develop ICT networks for public and private universities and polytechnics as well as research and education networks in Indonesia. - Prepare master plan for ICT human resource development in Indonesia. - Develop and implement ICT curricula. - Use ICT as an essential part of the curricula and learning tools in schools/universities and training centers. - Establish distance education programs including participation in Global Development Learning and other networks (e.g. J-NET). - Conduct ICT skills training for government employees. - Conduct training on facilitating e-commerce standard (UNCITRAL) for implementation. - Extend and further develop SME ICT awareness program and incubators. - Facilitate the use of internet for more efficient teaching and learning (e.g. School 2000). - Establish an efficient support and facilitation scheme for the procuring/financing/conducting of ICT skills training and capacity. - Develop Indonesian language-based man-machine interface as well as applications and contents. | 2001-2003 2001-2005 2001-2005 2001-2003 2002-2004 2001-2005 2001-2005*) 2001-2005 2001-2003 2001-2003 2002-2005*) 2002-2005 2002-2004 | B B A B A B A A B B A B A | Min. of Industry and Trade, Min. of Research and Technology, Min. of National Education, universities, private sector Min. of National Education, Min. of Industry and Trade, universities, national institutes of sciences, private sector Min. of National Education, Min. of Research and Technology, universities, internet and telecommunication operators, private sector Min. of Research and Technology, Min. of National Education, TKTI Min. of National Education Min. of National Education, schools, universities, private sector Min. of National Education, Min. of Research and Technology, Min. of Hearlth and Social Welfare, universities, private sector TKTI, all ministries, local governments Min. of Communications, Min. of Industry and Trade, Min. of Research and Technology Min. of Research and Technology, Min. of Industry and Trade, CCI, local governments Min. of National Education, schools, universities, private sector local governments, private sector Min. of Research and Technology, BPPT | Japan: (a) Improving ICT education and R&D in higher education through: (i) technical cooperation project with Electronic Engineering Polytechnic Institute of Surabaya (EEPIS) from October 1999 to September 2004, (ii) providing equipment and facilities to EEPIS for establishing D4 course in information technology engineering. (b) ICT related training courses are scheduled to start. (c) J-Net Project – Distance Technical Cooperation –, J-Net Satellite Center to be operated within FY2002. WB: (a) Global Distance Learning Network – GDLN – as part of ICT support to the Bank’s education sector, (b) Support for expansion of BPPT IPTEKnet under IIDP, (c) Socialization of the IT Framework through workshops for government employees under the IIDP. AUSAID: (a) Training for local governments: technical assistance to Min. of Home Affairs and regional finance management information system to manage fiscal decentralization with Min. of Finance, (b) Radio program Kang Guru In the Classroom accessible via website and magazines are distributed in the classrooms of five largest Indonesian cities, (c) CDROMS of Bulletin of Indonesian Economic Studies distributed to libraries and teaching centers. Planned activities: (a) NTT Primary Education Partnership: training teachers, teacher scholarships, district level education authorities capacity building and establish ‘education centers/teacher resource centers’ in 5 Flores cities. (b) Assess opportunities for assistance to develop policies and medium-term ICT implementation strategies for ICT in schools. |

- Infrastructure

| No. | ## Action Plan | Time Schedule | Priority | Implementing Agency | Donors’ Current Program |
| --- | --- | --- | --- | --- | --- |
|  | - Facilitate internet access to public services, such as schools, universities, and hospitals. - Progressively develop national backbone infrastructure and develop local access networks in underserved areas. - Implement universal access program and extend access beyond the market through a range of innovative public access initiatives, including new technologies and telecenters. - Optimize function of VSAT at Ministry of Home Affairs and Regional Autonomy, and Local Government. | 2001-2003 2001-2005 2001-2003 2001-2003 | B A A A | telecommunication and internet operators, schools, universities, hospitals, private sector Min. of Communications, telecommunication network providers, private sector Min. of Communications, Min. of Finance, local governments, telecommunication and internet operators, telematics society TKTI, Min. of Home Affairs and Regional Autonomy, local governments | WB: (a) Through BPPT, expansion of IPTEKnet’s public access network, (b) Through MTPT, developing a plan for the provision of rural telephone services on a commercial basis, (c) Through MOIT/TATP, pilot project to test VOIP to up to 500 Wartels with IIDP’s matching- grant program. Japan: Grant Assistance scheme to improve: (i) TVRI’s broadcasting equipment and (ii) MMTC’s (Multi Media Training Center) equipment. |

- Applications

| No. | ## Action Plan | Time Schedule | Priority | Implementing Agency | Donors’ Current Program |
| --- | --- | --- | --- | --- | --- |
| 4.1 | # Applications for the Government - Restructure government interaction system to achieve good governance. - Revitalize government portals to provide ease of use transparency and maximum consistency, fast downloads, rapid access to information, procedures and specific contacts. - Complete implementation of government online strategy prepared under IIDP and others. - Prepare government online action plan for each government agency. - Ensure easy access to essential public data in Indonesia. - Promote and develop electronic access to provide basic information, interaction, and services for citizens and government’s client community. - Develop applications that promote civil society and community participation in democratic and public activities. - Develop on-line submission of financial reports by public agencies. - Develop on-line submission of financial and transaction reports by tax entities. - Develop institutional and human resource development for ICT-related customs services. - Develop public services online (such as workforce, land use, conflict resolution, agriculture, export/import, telemedicine and health data center, and immigration information systems) to improve public services. - Implement MIS and decision support system in supporting decentralization process and assurance of minimum service standards and obligations under special funding provisions, inter-government loans and cooperation agreements. - Establish executive information system for national and local government, including 1) providing integrated information/database for state-owned companies (BUMN/D), and 2) increasing controlling mechanism for government to BUMN/D. - Enable public e-procurement for central and regional governments and their enterprises through establishment of appropriate framework for 1) business opportunities and contract awards, 2) quality standards on content and availability, 3) coding standards for normalization, cross referencing, and analysis of public procurement data. - Establish ID databank for industry/enterprise to provide digital certificate for industry/enterprise. - Enhance effectiveness use of broadcasting media for the distribution of information to remote and rural areas (including to computer illiterate people). - Develop e-television based interactive program through digital technology application in TV broadcasting. - Change the ID card system to a national card and database system and integrate with national demographic information systems. - Develop support system for government, legislature, and judicatory interaction. - Implement comprehensive e-government, e-business, and e-public infrastructure services as national pilot project (G2G, G2B, G2C) e.g. Batam Intelligent Island, Kemayoran Cyber City, etc. | 2001-2005 2001 2001-2003*) 2001-2002 2002-2003 2001-2005 2003-2005 2001-2005 2001-2005 2001-2005*) 2001-2003 2001-2003 2001-2005 2002-2005 2001-2005*) 2001-2005*) 2001-2004 2002-2005 2003-2005 2001-2005 | B B A B B B B B B A A B B A A A B B B A | Min. of Administrative Reforms TKTI, all ministries TKTI, other government agencies All government agencies, TKTI TKTI, Min. of Home Affairs and Regional Autonomy, local governments Min. of Communications, related ministries (based on information/services provided) Min. of Home Affairs, local governments Min. of Finance, local governments Min. of Finance Min. of Finance Min. of Home Affairs, Min. of Workforce and Transmigration, Min. of National Education, Min. of Finance, National Land Affairs Agency, Politics and Security Coordination Office, Indonesian Police, National Army, Min. of Agriculture, Min. of Forestry and Plantation, Min. of Industry and Trade, Min. of Health and Social Welfare, Central Agency for Statistics, Min. of Justice, local governments Min. of Home Affairs, local governments Min. of Finance, Min. of Home Affairs, central and local governments, state-owned enterprises Min. of Finance, National Development Planning Agency Min. of Industry and Trade, CCI, BARKI Min. of Communications, TVRI Min. of Communications, TVRI Min. of Home Affairs, Central Statistics Agency, local governments State Secretariat, Min. of Administrative Reforms, Min. of Justice, Supreme Court, Parliament BPPT, TKTI, BIDA, BPKK, CCI, private sector | WB: (a) Through MTAC, technical assistance to: (i) business model and pilot for electronic tourism and information services, (ii) identification and costing of promising on-line government projects (over 20 e-government pilot projects are identified under IIDP), (b) Through BPPT, support through infoDev grant program to IPTEKnet to develop a business plan for the Country Gateway and undertake certain tasks related to a pilot initiative in e-procurement. Japan: (a) E-Government: (i) developing a study for a master plan to create IT-based administrative services, (ii) project to improve customs services with funding from ODA loan and grant for the study to be carried out, (iii) considering a development study for a project to promote ICT in the administration of IP rights. CIDA: (a) Support to local government capacity building as a general advisor to APKASI, (b) Funding a short-term advisor to Batam Industrial Development Authority to assist with marketing and investment strategies. AUSAID: Legal Reform Program Facility – LRP – providing information from the short-term assistance (June 2001 – June 2003) in legal reform on the web. Planned activity: as part of LRP, to provide free public access to legal information on the web which will include audit law, treaties, research reports and legislative history. The goal is to encourage public participation in the law making process. |
| 4.2 | # Applications for Private Sector - Develop telecommunication/internet kiosks to implement Community Telecenter concept. - Extend regional electronic access to provide basic information tailored to local social and economic activities to promote the competitiveness of the region (e.g. Desa Maju). - Extend and improve the e-payment system (Indonesia Network Payment System) for greater speed, reliability, and lower cost catering for micro payments, including development of multipurpose smart card. - Prepare e-commerce standard applications for SMEs. - Provide trade facility, information, assistance center for development of SMEs. - Extend technical assistance and training funding support scheme for SMEs’ capacity improvement, including matching grant scheme. - Promote and assist more efficient industry market and logistics, including providing automotive industry solution center: 1) streamlining spare-parts and automotive distribution process, and 2) providing information system for small medium spare-parts supplier. - Facilitate and assist ICT application to market research marketing and trade for Indonesia industry and targeted market groups, including: 1) support local purchases by Indonesian Diaspora in the US and elsewhere to be supplied by Indonesian companies through a consolidated e-commerce web site/cybermall, 2) facilitate industry B2B e-commerce by leveraging industry-specific B2B vertical industry portals with a focus of expanding existing market share, 3) facilitate e-business, both B2B and B2G and associated opportunities, and 4) support overseas marketing via B2C e-commerce development of aggregated web sites (supported by catalogs with product, services, and transaction capabilities). | 2001-2005 2001-2005*) 2001-2003 2001-2003 2001-2003 2001-2003*) 2001-2003 2002-2005 | A A B B A A B B | Min. of Communications, local governments, private sector, telematics society Local governments, private sector, telematics society Min. of Finance, Central Bank, private sector Min. of Industry and Trade, CCI Min. of Industry and Trade, Min. of Finance, Min. of Cooperatives, CCI, private sector Min. of Industry and Trade Min. of Industry and Trade, private sector Min. of Industry and Trade, CCI, private sector | WB: (a) Through MOIT, cost-sharing grants to SMEs through the Technical Assistance and Training Program (TATP) to make ICT consulting and training services more affordable and accessible. Demand has far exceeded budget, and initial impact assessments are encouraging. (b) With USAID, video-conference on telecenter best practices. (c) Through MTAC, technical assistance to facilitate private entry in the postal sector, (d) Through BPPT, development of new lines of business, and exploring ways to commercialize operations in a phased manner, (e) Tested SME e-commerce readiness methodology on potential user groups of e-commerce in Indonesia. AUSAID: (a) The Australia Indonesia Development Area (AIDA) Business Directory: website to provides businesses with a range of information on SME size businesses located within AIDA to facilitate development opportunities. Japan: Promotion of ICT industries through: (i) extending the activities of Indonesia Export Training Center (IETC): considering a technical cooperation project to promote export of rural industries, (ii) considering a development study for ICT industry. USAID: Planned activities: survey on Warnets and potential Community Tele-Center (CTC) development, publication of a CTC guidebook for Indonesia, and facilitating access and content pilot projects (USAID DOT-COM partnership). ADB: TA to support the banking sector efforts led by Bank Indonesia in establishing a Credit Information System. Swisscontact: (a) Support to establish an internet-based Info-Platform for BDS providers that will provide access to information on their services and serve as an exchange platform. (b) TAF and Swisscontact are supporting the initiative of Fornas (National SME Forum) to establish a business-network platform among the regional SME Forums (Forda). |

Note:

*) : on-going program

A : first priority (urgent)

B : second priority (important)